Sprint 5 Planning Notes

Official Website and Customer Enquiry Management System for a UK Auto Parts SME

1. Document Control

| Field | Details |
| --- | --- |
| Client display name | Auto Parts SME |
| Phase | Phase 2: SQL and Power BI Reporting Enhancement |
| Sprint | Sprint 5: SQL Data Build |
| Sprint duration | 01 June 2026 to 12 June 2026 |
| Prepared by | Business Analyst |
| Document date | 01 June 2026 |
| Version | 1.0 |
| Status | Completed as Sprint 5 planning evidence |

2. Purpose of This Document

This document records the start of Sprint 5 after Phase 2 approval. It confirms the sprint goal, planned backlog, ownership, story points, expected outputs, and Jira and Confluence updates needed for the SQL data build work.

This planning note is created during Sprint 5 planning. It is not a separate project document required before the sprint starts. In a real Agile team, the backlog is prepared before the sprint, and this planning note is completed at the start of the sprint.

3. Sprint Summary

| Item | Details |
| --- | --- |
| Sprint name | Sprint 5: SQL Data Build |
| Sprint status | Active |
| Duration | 01 June 2026 to 12 June 2026 |
| Total backlog items | 12 |
| Total planned story points | 30 |
| Sprint goal | Build the SQL data foundation for customer enquiry and lead tracking dashboard. |
| Main output | SQL tables, sample data, SQL reporting views, validation evidence, and Power BI readiness review. |

4. Sprint 5 Scope

• Create the SQL data structure for customer enquiry, quote request, lead status, follow-up note, enquiry source, product category, and newsletter subscription data.

• Prepare sample enquiry and quote request data for testing and reporting validation.

• Create SQL views or reporting-ready outputs that can support the Sprint 6 Power BI dashboard.

• Review SQL build against approved Phase 2 data requirements.

• Run SQL validation checks before dashboard work starts.

• Confirm that SQL output is ready for Power BI dashboard development in Sprint 6.

5. Out of Scope for Sprint 5

• Final Power BI dashboard build is not included in Sprint 5.

• Customer login, payment, checkout, live inventory, and external API integration are not included.

• No real customer data will be used in portfolio evidence.

• Final Phase 2 business sign-off will happen after Sprint 6 dashboard UAT.

6. Next 2 Hours Work by Role

| Team member | Next 2 hours job | Why this is needed |
| --- | --- | --- |
| Scrum Master | Confirm sprint goal, scope, delivery plan, and blockers. | To start the sprint with clear direction and reduce delivery confusion. |
| Product Owner | Confirm priority of SQL build items. | To make sure the team works on the highest-value data foundation first. |
| Business Analyst | Complete Sprint 5 planning notes and confirm user stories are ready. | To provide clear delivery evidence and avoid unclear requirements. |
| Business Owner | Confirm reporting value for enquiry and lead tracking. | To ensure the SQL build supports business decision making. |
| Data Developer | Review required tables, fields, and relationships. | To prepare SQL structure before writing scripts. |
| QA Tester | Review SQL validation needs and expected test checks. | To prepare testing before data build is completed. |
| Power BI Developer | Review required SQL output for dashboard KPIs. | To ensure Sprint 6 dashboard can connect to correct reporting fields. |
| DevOps | Confirm where SQL scripts and project files will be stored. | To support version control and controlled handover. |

7. Sprint 5 Backlog and Story Points

| No. | Type | Backlog item | Owner | SP | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Task | Prepare Sprint 5 Planning Notes | Business Analyst | 2 | In Progress at start, Done after this document is attached |
| 2 | Task | Prepare SQL Build User Stories and Acceptance Criteria | Business Analyst | 2 | To Do |
| 3 | Task | Create ERD / Data Relationship Diagram | Data Developer | 3 | To Do |
| 4 | Story | Create SQL Tables for Enquiry and Lead Tracking | Data Developer | 5 | To Do |
| 5 | Story | Add Sample Enquiry and Quote Request Data | Data Developer | 3 | To Do |
| 6 | Story | Create SQL Views for Power BI Reporting | Data Developer | 5 | To Do |
| 7 | Task | Review SQL Build Against Data Requirements | Business Analyst | 3 | To Do |
| 8 | Task | Run SQL Validation Checks | QA Tester | 3 | To Do |
| 9 | Task | Review SQL Output for Power BI Readiness | Power BI Developer | 2 | To Do |
| 10 | Task | Prepare Sprint 5 Review Notes | Business Analyst / Scrum Master | 1 | To Do |
| 11 | Task | Prepare Sprint 5 Retrospective Notes | Scrum Master / Team | 1 | To Do |
| 12 | Task | Prepare Sprint 5 Closure Summary | Business Analyst / Scrum Master | 2 | To Do |

8. Key Dependencies

| Dependency | Impact if not ready | Owner |
| --- | --- | --- |
| Approved Phase 2 SQL Data Requirement Document | SQL build may not match reporting needs. | Business Analyst |
| Confirmed field list and data rules | Developer may build incomplete tables or incorrect relationships. | Business Analyst / Data Developer |
| ERD or logical data relationship view | SQL tables may be built without clear relationships. | Data Developer |
| Sample data rules | QA and Power BI review may not be realistic. | Business Analyst / QA |
| Power BI KPI requirements | SQL views may miss required dashboard fields. | Power BI Developer |

9. Risks and Controls

| Risk | Control action | Owner |
| --- | --- | --- |
| SQL tables do not support dashboard KPIs. | Power BI Developer reviews required output before SQL views are finalised. | Power BI Developer |
| Data fields are unclear. | Business Analyst confirms field definitions and rules before SQL build starts. | Business Analyst |
| Validation is left too late. | QA Tester reviews SQL validation plan during sprint start. | QA Tester |
| Portfolio evidence includes sensitive details. | Use only anonymised project name and sample data. | Business Analyst |
| ERD and SQL scripts do not match. | Data Developer reviews ERD before table build and BA checks against requirement document. | Data Developer / BA |

10. Jira Update Required

| Jira item | Update |
| --- | --- |
| Sprint 5: SQL Data Build | Status is Active. Duration is 01 June 2026 to 12 June 2026. |
| Prepare Sprint 5 Planning Notes | Move from In Progress to Done after attaching this document. |
| Prepare SQL Build User Stories and Acceptance Criteria | Keep in To Do. This is the next task. |
| Remaining Sprint 5 items | Keep in To Do until their work starts. |

11. Confluence Update Required

Update Confluence page: Phase 2 - Sprint 5 SQL Data Build.

• Add sprint name, duration, sprint goal, total backlog items, and total story points.

• Add or attach this Sprint 5 Planning Notes document.

• Add the Jira sprint link or mention the Jira sprint name.

• Record that Sprint 5 is active and the first planning task is completed.

12. Interview Explanation

In Sprint 5, I supported sprint planning after Phase 2 approval by confirming the sprint goal, backlog items, story points, owners, risks, dependencies, and planned outputs. The sprint focused on SQL data build so that enquiry and lead tracking data could be validated before Power BI dashboard development started in Sprint 6.